## WFP-2r9 DRAFT 12-14-09
WHOLE FARM PLAN SUMMARY and WFP-2: BMP BUDGET & PROJECTED IMPLEMENTATION
WFP-2 | [19 empty] | LF Team
Landowner's and/or Producer's Name: |  |  | Farmer Jones | [5 empty] | County: Greene |  | Agreement No.: |  |  | GRS-000 |  |  | Date:
Best Management Practice (BMP) |  |  | NRCS / WAC Code | Units Planned | Prior Planning Estimate | Revised Planning Estimate | Funds Requested | Units Completed | Date Completed | Funds Expended to Date | Projected Implementation | [7 empty] | NU - New and/or Unfunded | Revision Description
Phase III
# | Location | Name (Life Span) | [8 empty] | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014
I. Parasites & Phosphorus - Animal Waste Storage |  |  | Existing inground animal waste storage facility not constructed to NRCS standards and specifications. Located in highly permeable soil type (Barbour) with known water table at 4.5 ft depth. Existing facility not sized for present herd, causing periodic overland flow.
| Tract 000 | Waste Storage Structure (10) | [17 empty] | revision 1
2 | FS |  | 313 | 1 proj | 0 | 0 | 0 | [12 empty] | deleted
Waste Storage Structure (10)
2a | FS |  | 313 | 1 proj | 96026 | 96026 | 96026 | 1 proj | 1/14/98 | 96026 | [9 empty] | Complete
|  | Collection/Reception Pit (10) | [17 empty] | revision 2
2b | FS |  | 313 | 1 proj | 0 | 0 | 0 | [12 empty] | deleted
|  | Collection/Reception Pit Roof Extension (10) | WAC
2b1 | FS |  | 3050 | 1 proj | 69119 | 69119 | 69119 | 1 proj | 9/13/01 | 69119 | [9 empty] | Complete
Transfer Pump/Pipeline (10)
2c | FS |  | 313 | 1 proj | 29120 | 29120 | 29120 | 1 proj | 12/19/97 | 29120 | [9 empty] | Complete
Site Prep (10)
2d | FS |  | 313 | 1 proj | 5500 | 5500 | 5500 | 1 proj | 12/17/97 | 5500 | [9 empty] | Complete
Waste Storage Structure - reinvestment (10)
2e | FS |  | 313 | 1 proj | 0 | 200000 | 200000 | [12 empty] | new | bar: Phase III 2009
|  | Manure Spreader Truck (10) | WAC
27 | FS |  | 3430 | 1 | 0 | 80000 | 80000 | [12 empty] | new | bar: Phase III 2010
Closure of Waste Impoundment
| FS |  | 360 | 1 | 0 | 0 | 0 | completed w/ BMP 12 | [11 empty] | Complete
|  | Manure Spreader (5) | WAC
1 | FS |  | 3410 | 1 ea | 11994 | 11994 | 11994 | 1 ea | 5/5/97 | 11994 | [9 empty] | Complete
Present freestall housing system contains bedded pack which is not compatible with proposed liquid manure storage system.
Individual Free Stall (10)
5 | FS |  | WAC | 1 sys | 9611 | 9611 | 9611 | 1 sys | 9/25/97 | 9611 | [9 empty] | Complete
II. Pesticides - Storage Facilities, Mixing/Loading Areas
No problems identified; custom applicator used.
III. Phosphorus - Fertilizer Storage
Fertilizer is used as purchased.
IV. Parasites - Animal & Manure Management
Unacceptable levels of calf illness and mortality due to inadequate housing facilities.
|  | Solar Calf Barn (10) | WAC | [16 empty] | revision 5
6 | FS |  | 3110 | 1 proj | 0 | 0 | 0 | [12 empty] | deleted
|  | Solar Calf Barn (10) | WAC
6.1 | FS |  | 3110 | 1 proj | 51405.14 | 51405.14 | 51405.14 | 1 proj | 3/2/00 | 51405.14 | [9 empty] | Complete
|  | Solar Calf Barn (10) | WAC
6.2 | FS |  | 3110 | 1 proj | 0 | 0 | 0 | completed w/ BMP 6.1 | [11 empty] | Complete
|  | Solar Calf Barn (10) | WAC
6.3 | FS |  | 3110 | 1 proj | 0 | 0 | 0 | completed w/ BMP 6.1 | [11 empty] | Complete
|  | Solar Calf Barn (10) | WAC
6.4 | FS |  | 3110 | 1 proj | 0 | 0 | 0 | completed w/ BMP 6.1 | [11 empty] | Complete
|  | Concrete Floor/Storage Pad (10) | WAC
6.5 | FS |  | 3110 | 1 proj | 0 | 0 | 0 | completed w/ BMP 6.1 | [11 empty] | Complete
|  | Sidewalls and Doors (10) | WAC
6.6 | FS |  | 3110 | 1 proj | 0 | 0 | 0 | completed w/ BMP 6.1 | [11 empty] | Complete
|  | Stanchion Barn Improvement (10) | [17 empty] | revision 4
7 | FS |  | WAC | 1 proj | 0 | 0 | 0 | [12 empty] | deleted
V. Nutrient Management
More than 50% of acreage show high phosphorus levels.
| All | Nutrient Management Plan (1) | [8 empty] | Phase III 2009: 1/29/09
3 | Fields |  | 590 | 444.3 ac | 0 | 0 | 0 | bar: Phase III 2007 to Phase III 2014
| All | Waste Utilization (1) | [8 empty] | Phase III 2009: 1/29/09
4 | Fields |  | 633 | 444.3 ac | 0 | 0 | 0 | bar: Phase III 2007 to Phase III 2014
| All | Record Keeping (1) | [8 empty] | Phase III 2009: 1/29/09 |  | revision 8
23 | Fields |  | NY748 | 444.3 ac | 0 | 0 | 0 | [12 empty] | delete
| All | Waste Management System (1) | [17 empty] | revision 8
24 | Fields |  | 312 | 1 | 0 | 0 | 0 | [12 empty] | delete
Manure spread through HSA.
Subsurface Drainage (10)
13 | F1c |  | 606 | 300' | 0 | 0 | 0 | 505' | 1999-03-01 | L/O paid | [9 empty] | Complete
Cows pasturing in HSA due to underdeveloped spring overflow.
|  | Spring Development (10) | [5 empty] | partial | 2007-12-21 | 6840
14 | P2 |  | 574 | 1 proj | 10500 | 10500 | 10500 | final | 2008-05-30 | 3660 | [9 empty] | complete
VI. Nutrients - Concentrated Sources |  |  | Barnyard behind stanchion barn has upslope water entering from pasture via roadway. Surface water flows through barnyard area with potential to reach existing watercourses below. Lack of scraping barnyard has accumulated organic matter causing poor drainage and nutrient loss.
Heavy Use Area Protection (10)
8 | FS |  | 561 | 1 proj | 3118.75 | 3118.75 | 3118.75 | 100 cy | 9/29/98 | 3118.75 | [9 empty] | Complete
|  | Roofed Barnyard (10) | WAC | [16 empty] | code
8.1 | FS |  | 3010 | 50'x60' | 30000 | 135000 | 135000 | [12 empty] | cost / date | bar: Phase III 2010
Diversion (10)
10 | FS |  | 362 | 166' | 0 | 0 | 0 | 120 lf | completed w/ BMP 8 | [10 empty] | Complete
Laneway between freestall and milking parlor crosses main farm access road. Lack of hard surface prevents manure cleanup.
|  | Heavy Use Area Protection (10) | [17 empty] | revision 3
11 | FS |  | 561 | 1 proj | 0 | 0 | 0 | [12 empty] | deleted
|  | Heavy Use Area Protection (10) | [5 empty] | 1 proj | 1998-01-08 | 1300
11.1 | FS |  | 561 | 1 proj | 6590 | 6590 | 6590 | repair | 2001-05-18 | 5290 | [9 empty] | Complete
Roof runoff water from stanchion barn creates excess water in barnyard.
Roof Runoff Management System (10)
9 | FS |  | 558 | 1 proj | 0 | 0 | 0 | completed w/ BMP 12.2 | [11 empty] | Complete
Wash water from milkhouse and milking parlor are piped into inground manure pit. Insufficient capacity causes periodic overflow.
See Category I, BMP 2a
Corn and hay silage stored in ag bags on earthen site adjacent to open drainage leading to main stream. Area heavily traveled by farm equipment; deep ruts develop. Rainwater and dropped silage cause large pools of polluted runoff that flow toward existing drainage.
Heavy Use Area Protection (10)
11.2 | FS |  | 561 | 1 proj | 0 | 0 | 0 | completed w/ BMP 12.2 | [11 empty] | Complete
|  | Heavy Use Area Protection (10) | [17 empty] | revision 3
12 | FS |  | 561 | 1 proj | 0 | 0 | 0 | [12 empty] | deleted
Heavy Use Area Protection (10)
12.1 | FS |  | 561 | 1 proj | 3800 | 3800 | 3800 | 300' | 1997-12-18 | 3800 | [9 empty] | Complete
|  | Heavy Use Area Protection (10) | [5 empty] | repair | 2001-05-18 | 1000
12.2 | FS |  | 561 | 1 proj | 52066.85 | 52066.85 | 52066.85 | 1 proj | 1998-08-28 | 51066.85 | [9 empty] | Complete
Heavy Use Area Protection (10)
12.3 | FS |  | 561 | 1 proj | 10000 | 15000 | 0 | [11 empty] | x - 2011 | cost / date
VII. Sediment - Diffuse
Cropland fields exhibit gullying and overland flow during storm events.
|  | Diversion (10) | [5 empty] | 200' div
15a | F1e |  | 362 | 675' | 9838.9 | 9838.9 | 9838.9 | 1140' tile | 1998-06-01 | 9838.9 | [9 empty] | Complete
Diversion (10)
15b | F1d |  | 362 | 1475' | 0 | 0 | 0 | completed w/ BMP 15a | [11 empty] | Complete
Stripcropping (1)
16 | F1c |  | 586 | 4.4 ac | 0 | 0 | 0 | [11 empty] | x - 2011 | date
Stripcropping (1)
25 | F5 |  | 585 | 25 ac | 0 | 0 | 0 | [11 empty] | x - 2011 | date
Subsurface Drainage (10)
26 | F5 |  | 606 | 4000 ft | 24000 | 24000 | 0 | [11 empty] | x - 2011 | date
Stripcropping (1)
28 | F4-7 |  | 585 | 38 ac | 0 | 0 | 0 | [11 empty] | x - 2012 | new
Obstruction Removal (10)
29 | F4-7 |  | 500 | 2,300' | 0 | 11500 | 0 | [11 empty] | x - 2012 | new
Subsurface Drainage (10)
30 | F4-7 |  | 606 | 4,000' | 0 | 24000 | 0 | [11 empty] | x - 2012 | new
Pasture 1c exhibits large areas of overland flow, causing sediment and nutrient movement from storage area into watercourse.
Stripcropping (1)
21 | F1d-f |  | 585 | 6.5 ac | 0 | 0 | 0 | 6.5 ac | 1998-08-31 | 0 | [9 empty] | Complete
Stripcropping (1)
22 | F1a, b |  | 585 | 7.0 ac | 0 | 0 | 0 | 7.0 ac | 1998-08-31 | 0 | [9 empty] | Complete
| All | Crop Rotation (1)
17 | Tracts |  | 328 | 444 ac | 0 | 0 | 0 | [12 empty] | date | bar: Phase III 2012
Diversion with Tile Outlet (10)
18 | P2 |  | 362 | 300' | 15000 | 15000 | 15000 | [12 empty] | date | bar: Phase III 2009
| All | Conservation Tillage (1)
31 | Tracts |  | 329 | 444 ac | 0 | 0 | 0 | [12 empty] | new | bar: Phase III 2010
VIII. Sediment - Concentrated
Cropland fields exhibit gullying and overland flow during storm events.
See Category VII
IX. Pesticides - Field & Animal Application
Pesticides currently used. Need to utilize NPURG to guide pesticide use and selection.
Pest Management (1)
19 |  |  | 595 | 217 ac | 0 | 0 | 0 | 217 ac | 1998-07-29 | 0 | [9 empty] | Complete
X. Fuel Storage |  |  | Four above ground portable fuel tanks (2 diesel: 250 & 300 gallon and 2 gasoline: both 275 gallon) need replacement with 1-500 gallon diesel tank w/concrete pad and 1-500 gallon gasoline tank.
|  | Farm Fuel Facility (10) | WAC
20 |  |  | 3310 | 1 | 7000 | 0 | 0 | [11 empty] | x - 2015
XI. Other Materials
Household and farm solid waste disposed of at landfill.
Total Planning Prior Estimate |  |  |  |  | 444689.64 |  |  |  | Total Paid | 358689.64 | Phase III 2007: Comments:; Phase III 2009: Cost Guideline:
Total Revised Planning Estimate | [5 empty] | 863189.64 |  |  |  |  | Phase III 2009: Funds requested over under cost guideline.
Total Funds Requested for Approval at this Time | [6 empty] | 788689.64 |  |  |  | Phase III 2009: Last Approval Date:
Supplemental WAP CREP Funding
V. Nutrient Management
Riparian Forest Buffer
32 | P1 |  | 391a | 7 ac | 0 | 0 | 0 | bar: Phase III 2012
Water Facility - Spring Development
33 | P1 |  | 574 | 1 sys | 23000 | 23000 | 11500 | bar: Phase III 2011
Fence
34 | P1 |  | 382 | 3800' | 9600 | 9600 | 4800 | bar: Phase III 2011
Tree and Shrub Establishment
35 | P1 |  | 612 | 2 ac | 4100 | 4100 | 2050 | bar: Phase III 2011
Total for CREP |  |  |  |  | 0 | 0 | 18350 |  | CREP Total Paid | 0
Funds Requested at 50% of eligible cost, USDA will pay remaining 50%.
Grand Total |  |  |  |  | 444689.64 | 863189.64 | 807039.64 |  | Grand Total Paid | 358689.64
PARTICIPANT CERTIFICATION
Signature of Landowner |  |  |  |  | Date | Signature of Producer (if applicable) |  |  |  |  | Phase III 2007: Date; Phase III 2009: Projected implementation is contingent upon the availability of funding.
REVIEWING OFFICIALS SIGNATURES
Planning Team Certification |  |  |  |  | Date | SWCD Review |  |  |  |  | Phase III 2007: Date
WAC Program Manager Certification |  |  |  |  | Date | WAC Executive Director Certification |  |  |  |  | Phase III 2007: Date
Planning Staff |  |  | Subsequent Funding Approvals |  |  |  | Ag Program Committee Funding Approval |  |  |  | Phase III 2007: Executive Committee Funding Approvals; Phase III 2014: WAC Funding Approvals
USDA Natural Resources Conservation Service
FOR OFFICE USE ONLY Comments: